# WCVS – Project Management Overview

Team Members: Logan Cribbs, Chhi Ly

Sponsor: Becky Buri

## Introduction

The project management plan for the WCVS Veteran e-Post Hub outlines how the development team, consisting of Logan Cribbs and Chhi Ly, will organize and manage work over three sprints during the semester. It defines the project timeline, task assignments, and identifies risks to ensure the website’s successful completion. Using Agile sprint cycles, version control through GitHub, and weekly coordination meetings, the team will monitor progress, address risks proactively, and maintain clear communication to deliver a functional and deployable system by the end of the term.

## Project Timeline

| Sprint | Weeks | Focus Area | Key Deliverables | Milestones |
| --- | --- | --- | --- | --- |
| Sprint 1 – Foundation & Setup | Weeks 1 – 5 | Project environment setup, dependency updates, tech-stack configuration, and initial documentation. | Working GitHub repo, Next.js + HeroUI migration, Tailwind setup, functional requirements, WRS draft. | Repo configured & WRS approved. |
| Sprint 2 – Core Development & Integration | Weeks 6 – 10 | UI design integration, event upload system, database schema setup, and resource tab completion. | Functional UI prototype, Prisma + SQLite DB, admin login & event upload working. | First full demo build ready. |
| Sprint 3 – Testing, Deployment & Presentation | Weeks 11 – 15 | Testing with Vitest, final bug fixes, deployment to Vercel, sprint report & presentation prep. | Fully deployed e-Post Hub + presentation slides & video. | Final submission & project close-out. |

## Task Assignment

| Task ID | Task Description | Assigned To | Due Week | Dependencies |
| --- | --- | --- | --- | --- |
| T-01 | Set up GitHub repo & branch structure | Chhi Ly | Week 1 | — |
| T-02 | Configure Next.js | Logan Cribbs | Week 2 | T-01 |
| T-03 | Draft Functional & Non-Functional Requirements + WRS | Team | Week 3 | T-01 |
| T-04 | Design UI mockups / integrate Figma layout → React | Team | Week 5 | T-02 |
| T-05 | Build database schema using Prisma + SQLite | Logan Cribbs | Week 7 | T-03 |
| T-06 | Implement admin login + Zod validation | Logan Cribbs | Week 8 | T-05 |
| T-07 | Create event upload + resource tab components | Chhi Ly | Week 9 | T-04 + T-05 |
| T-08 | Test features using Vitest | Team | Week 12 | T-06 + T-07 |
| T-09 | Fix bugs and validate UI alignment with prototype | Team | Week 13 | T-08 |
| T-10 | Deploy final build to Vercel & prepare presentation | Team | Week 15 | T-09 |

## Risk Registry

| Risk ID | Description | Impact | Likelihood | Mitigation Strategy |
| --- | --- | --- | --- | --- |
| R-01 | Deprecated NextUI packages break UI build | Medium | High | Replace with HeroUI early & test UI rendering each sprint |
| R-02 | Workload imbalance | High | low | Split frontend / backend tasks by strengths & meet weekly |
| R-03 | Prisma schema migration errors | High | Medium | Use migration history & frequent DB backups |
| R-04 | UI design inconsistency with Figma | Medium | Medium | Peer review each page before merge to main |
| R-05 | Time conflicts with school / work | High | Medium | Set joint weekly progress check-ins + Slack reminders |
| R-06 | Deployment issues on Vercel | Medium | Low | Stage deploy before final & document fixes |